## Project Info
AI-Driven Multi-Agent Negotiation Training & Simulation Platform — Agile Tracker
Legend: fill only the white/unshaded rows below each header on every sheet. Header rows and shaded cells should not be edited.
Project Name | Creation of AI Driven Multi-Agent Negotiation Training & Simulation Platform
Repository | https://github.com/adarshmichael/ai-multi-agent-negotiation
Team | Team-1
Team Lead | Arun
Team Members | Arun (TL), Adarsh, Anusha
Program | Infosys Springboard Virtual Internship 7.0
Agile Approach | Agile / Scrum-style
Duration | 8 weeks / 4 sprints
Sprint 1 Start Date | 19-Aug-2026
Modes | Simulation Mode (AI vs AI); Practice Mode (Human vs AI)
Scenarios | Vendor Pricing Negotiation; Job Offer Negotiation; Project Budget Allocation
Core Modules | Scenario & Agent Configuration; Orchestrator; LLM Reasoning; Counteroffer Evaluation; Deadlock Detection; Negotiation Arena; Practice Mode; Outcome Report

## Product Backlog
Planned Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
1 | US1 | As a team, we want to design the basic negotiation system workflow and agent personas so that we understand the core concept before implementation. | Must Have | - | Team | Done
1 | US2 | As a team, we want to finalize agent personas and complete the Agent Configuration UI so that scenarios automatically load their agents. | Must Have | US1 | Team | Done
1 | US3 | As a team, we want to build the negotiation state model, offer structure, decision logic, concession tracking and orchestrator interface so the negotiation engine has a strong foundation. | Must Have | US2 | Team | Done
1 | US4 | As a team, we want to add the MIT License and maintain Agile documentation in our GitHub repository so the project meets submission requirements. | Should Have | US3 | Team | In Progress
2 | US5 | As a user, I want AI agents to use an LLM (Gemini) reasoning engine so that offers and responses are generated from persona, goals and full negotiation history. | Must Have | US3 | TBD | Done
2 | US6 | As a user, I want to see each agent's internal reasoning and extracted parameters on its stat card so the negotiation feels transparent. | Should Have | US5 | TBD | Done
2 | US7 | As a developer, I want a rule-based mock engine fallback so the UI can be tested deterministically without a live API key. | Should Have | US5 | TBD | Done
2 | US8 | As a developer, I want the AI-vs-AI negotiation loop tested end-to-end across all three scenario templates. | Must Have | US5 | TBD | In Progress
3 | US9 | As a user, I want to see the negotiation as a live, chat-style transcript with round-by-round updates. | Must Have | US5 | TBD | To Do
3 | US10 | As a user, I want to see live agent stance indicators and round metrics while a negotiation runs. | Medium | US9 | TBD | To Do
3 | US11 | As a user, I want to negotiate directly against AI agents in Practice Mode by typing my own offers. | Must Have | US5 | TBD | To Do
3 | US12 | As a user, I want stalled negotiations to be detected after N rounds and either resolved or ended. | Medium | US9 | TBD | To Do
4 | US13 | As a user, I want a final outcome screen showing agreement terms, concession timeline and per-agent objective satisfaction. | Must Have | US9,US11 | TBD | To Do
4 | US14 | As a user, I want to download the negotiation transcript and a structured summary report. | Should Have | US13 | TBD | To Do
4 | US15 | As a developer, I want end-to-end testing across both modes, all scenarios and all personality combinations. | Must Have | US13 | TBD | To Do
4 | US16 | As a team, we want complete technical documentation and a final demonstration prepared. | Must Have | US15 | Team | To Do
Backlog Progress |  | Done: | 6 / 16

## Sprint Backlog
NOTES: Task sizing should be between 0.5 and 12 hours. Add a new SPRINT block for each sprint.
US ID | Task ID | Task Description | Start Date/Time | Completion Date/Time | Team Member | Activity | Status | Estimate (Hrs)
SPRINT 1 BACKLOG
US1 | T1 | Understand multi-agent negotiation concept, AI agent role, Simulation vs Practice mode | 2026-08-21 10:00 | 2026-08-21 11:00 | Arun | Research | Completed | 1
US1 | T2 | Design basic system workflow diagram (Scenario Selection to Outcome Report) | 2026-08-21 11:00 | 2026-08-21 12:30 | Adarsh | Design | Completed | 1.5
US1 | T3 | Define agent personas (Role, Goal, Constraint, Personality) for at least 2 agents | 2026-08-21 12:30 | 2026-08-21 14:00 | Anusha | Design | Completed | 1.5
US1 | T4 | Select negotiation scenario and define the two negotiating parties' objectives | 2026-08-21 14:00 | 2026-08-21 15:00 | Arun | Design | Completed | 1
US1 | T5 | Prepare basic Agent Configuration UI wireframe | 2026-08-21 15:00 | 2026-08-21 17:00 | Adarsh | Design | Completed | 2
US2 | T6 | Finalize agent personas (role, goal, constraint, personality) for all 3 scenarios | 2026-08-25 10:00 | 2026-08-25 12:00 | Anusha | Design | Completed | 2
US2 | T7 | Complete Agent Configuration UI - display each agent as a role card | 2026-08-25 12:00 | 2026-08-25 15:00 | Adarsh | Development | Completed | 3
US2 | T8 | Connect scenario selection so it auto-loads predefined agents, roles, goals, constraints | 2026-08-25 15:00 | 2026-08-25 17:00 | Arun | Development | Completed | 2
US2 | T9 | Finalize system architecture diagram (User to Outcome Report flow) | 2026-08-25 17:00 | 2026-08-25 18:30 | Adarsh | Design | Completed | 1.5
US2 | T10 | Push completed implementation to GitHub with identifiable contributions | 2026-08-25 18:30 | 2026-08-25 19:30 | Arun | GitHub | Completed | 1
US3 | T11 | Create Negotiation State Model (scenario, round, turn, offers, status, goals, constraints, personality) | 2026-08-31 10:00 | 2026-08-31 12:00 | Arun | Development | Completed | 2
US3 | T12 | Define standard Offer Structure (value/terms, agent, round, reason, timestamp) | 2026-08-31 12:00 | 2026-08-31 13:00 | Anusha | Design | Completed | 1
US3 | T13 | Implement rule-based Accept / Reject / Counteroffer decision logic | 2026-08-31 13:00 | 2026-08-31 15:30 | Adarsh | Development | Completed | 2.5
US3 | T14 | Implement concession tracking across negotiation rounds | 2026-08-31 15:30 | 2026-08-31 17:00 | Anusha | Development | Completed | 1.5
US3 | T15 | Prepare basic Orchestrator interface (turn, round, history, state, next agent) | 2026-08-31 17:00 | 2026-08-31 19:00 | Arun | Development | Completed | 2
US3 | T16 | Connect existing Scenario/Agent Configuration UI to Negotiation State | 2026-08-31 19:00 | 2026-08-31 20:30 | Adarsh | Development | Completed | 1.5
US3 | T17 | Push Milestone 1 negotiation engine foundation to GitHub | 2026-08-31 20:30 | 2026-08-31 21:30 | Arun | GitHub | Completed | 1
US4 | T18 | Add MIT License to the team's GitHub repository | 2026-08-31 21:30 | 2026-08-31 22:00 | Anusha | Documentation | Completed | 0.5
US4 | T19 | Prepare Agile documentation in repository as per reference Google Drive folder | 2026-09-01 10:00 | 2026-09-01 12:00 | Arun | Documentation | In Progress | 2
SPRINT 2 BACKLOG
US5 | T20 | Build NegotiationEngine.js orchestrator loop (turn order, history, state, round count) |  |  | TBD | Development | Completed
US5 | T21 | Integrate Google Gemini LLM Decision Provider with agent persona/goals/constraints |  |  | TBD | Development | Completed
US5 | T22 | Define structured JSON response schema (decision, offer, message, reasoning, parameters) |  |  | TBD | Development | Completed
US6 | T23 | Surface agent REASONING and PARAMETERS on live stat cards in the UI |  |  | TBD | Development | Completed
US7 | T24 | Build rule-based mock engine fallback for deterministic testing without an API key |  |  | TBD | Development | Completed
US8 | T25 | Run and confirm AI-vs-AI negotiation loop across all 3 scenario templates |  |  | TBD | Testing | In Progress
SPRINT 3 BACKLOG
USx | Tx | Example: describe the task |  |  | Team member name | Design / Development / Testing / Documentation / GitHub | To Do | 1
SPRINT 4 BACKLOG
USx | Tx | Example: describe the task |  |  | Team member name | Design / Development / Testing / Documentation / GitHub | To Do | 1

## Standup Log
Daily / per-session standup — add one row per team member per check-in
Date | Sprint | Team Member | Yesterday / Since Last Update | Today / Next | Impediments
19-Aug-2026 | 1 | Arun | Kicked off project research | Design system workflow diagram | None

## Bug Tracker
Bug ID | Date Found | Sprint | Description | Severity | Assigned To | Status | Resolution / Remarks
BUG-01 | [5 empty] | Open
BUG-02 | [5 empty] | Open
BUG-03 | [5 empty] | Open
BUG-04 | [5 empty] | Open
BUG-05 | [5 empty] | Open
BUG-06 | [5 empty] | Open
BUG-07 | [5 empty] | Open
BUG-08 | [5 empty] | Open
BUG-09 | [5 empty] | Open
BUG-10 | [5 empty] | Open

## Retrospective
Sprint | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 |  |  | Arun
1 |  |  | Adarsh
1 |  |  | Anusha
2 |  |  | Arun
2 |  |  | Adarsh
2 |  |  | Anusha
3 |  |  | Arun
3 |  |  | Adarsh
3 |  |  | Anusha
4 |  |  | Arun
4 |  |  | Adarsh
4 |  |  | Anusha

## Definition of Done
Checklist Item | Done?
Requirement implemented | No
Code integrated to main branch | No
Feature tested (manual or automated) | No
Acceptance criteria satisfied | No
Known bugs fixed or documented in Bug Tracker | No
Relevant scenario(s) tested (Vendor Pricing / Job Offer / Project Budget) | No
Documentation updated (README / docs folder / Agile tracker) | No