## Project Info
Field | Details
Project Name | Creation of AI Driven Multi-Agent Negotiation Training & Simulation Platform
Team | Team-1
Team Lead | Arun
Team Members | Arun (TL), Adarsh, Anusha
Program | Infosys Springboard Virtual Internship 7.0
Sprint 1 Start Date | 19-Aug-2026

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | Actual | US1 | As a team, we want to design the basic negotiation system workflow and agent personas so that we understand the core concept before implementation. | Must Have | - | Team | Done
1 | Actual | US2 | As a team, we want to finalize agent personas and complete the Agent Configuration UI so that scenarios automatically load their agents. | Must Have | US1 | Team | Done
1 | Actual | US3 | As a team, we want to build the negotiation state model, offer structure, decision logic, concession tracking and orchestrator interface so the negotiation engine has a strong foundation. | Must Have | US2 | Team | Done
1 | Actual | US4 | As a team, we want to add the MIT License and maintain Agile documentation in our GitHub repository so the project meets submission requirements. | Should Have | US3 | Team | Done

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Duration Since Previous Task (Hrs)
[8 empty] | 30.5 | 0 | 0 | 7 | 0 | 0 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 12 | 2
SPRINT 1 BACKLOG
US1 | T1 | Understand multi-agent negotiation concept, AI agent role, Simulation vs Practice mode | 2026-08-21 10:00 | 2026-08-21 11:00 | Arun | Research | Completed | 1 | [14 empty] | 0 | bar: Day 3
US1 | T2 | Design basic system workflow diagram (Scenario Selection to Outcome Report) | 2026-08-21 11:00 | 2026-08-21 12:30 | Adarsh | Design | Completed | 1.5 | Day 3: 1.5 | 0
US1 | T3 | Define agent personas (Role, Goal, Constraint, Personality) for at least 2 agents | 2026-08-21 12:30 | 2026-08-21 14:00 | Anusha | Design | Completed | 1.5 | Day 3: 1.5 | 0
US1 | T4 | Select negotiation scenario and define the two negotiating parties' objectives | 2026-08-21 14:00 | 2026-08-21 15:00 | Arun | Design | Completed | 1 | [14 empty] | 0 | bar: Day 3
US1 | T5 | Prepare basic Agent Configuration UI wireframe | 2026-08-21 15:00 | 2026-08-21 17:00 | Adarsh | Design | Completed | 2 | Day 3: 2 | 0
US2 | T6 | Finalize agent personas (role, goal, constraint, personality) for all 3 scenarios | 2026-08-25 10:00 | 2026-08-25 12:00 | Anusha | Design | Completed | 2 | Day 7: 2 | 89
US2 | T7 | Complete Agent Configuration UI - display each agent as a role card | 2026-08-25 12:00 | 2026-08-25 15:00 | Adarsh | Development | Completed | 3 | Day 7: 3 | 0
US2 | T8 | Connect scenario selection so it auto-loads predefined agents, roles, goals, constraints | 2026-08-25 15:00 | 2026-08-25 17:00 | Arun | Development | Completed | 2 | Day 7: 2 | 0
US2 | T9 | Finalize system architecture diagram (User to Outcome Report flow) | 2026-08-25 17:00 | 2026-08-25 18:30 | Adarsh | Design | Completed | 1.5 | Day 7: 1.5 | 0
US2 | T10 | Push completed implementation to GitHub with identifiable contributions | 2026-08-25 18:30 | 2026-08-25 19:30 | Arun | GitHub | Completed | 1 | [14 empty] | 0 | bar: Day 7
US3 | T11 | Create Negotiation State Model (scenario, round, turn, offers, status, goals, constraints, personality) | 2026-08-31 10:00 | 2026-08-31 12:00 | Arun | Development | Completed | 2 | Day 13: 2 | 134.5
US3 | T12 | Define standard Offer Structure (value/terms, agent, round, reason, timestamp) | 2026-08-31 12:00 | 2026-08-31 13:00 | Anusha | Design | Completed | 1 | [14 empty] | 0 | bar: Day 13
US3 | T13 | Implement rule-based Accept / Reject / Counteroffer decision logic | 2026-08-31 13:00 | 2026-08-31 15:30 | Adarsh | Development | Completed | 2.5 | Day 13: 2.5 | 0
US3 | T14 | Implement concession tracking across negotiation rounds | 2026-08-31 15:30 | 2026-08-31 17:00 | Anusha | Development | Completed | 1.5 | Day 13: 1.5 | 0
US3 | T15 | Prepare basic Orchestrator interface (turn, round, history, state, next agent) | 2026-08-31 17:00 | 2026-08-31 19:00 | Arun | Development | Completed | 2 | Day 13: 2 | 0
US3 | T16 | Connect existing Scenario/Agent Configuration UI to Negotiation State | 2026-08-31 19:00 | 2026-08-31 20:30 | Adarsh | Development | Completed | 1.5 | Day 13: 1.5 | 0
US3 | T17 | Push Milestone 1 negotiation engine foundation to GitHub | 2026-08-31 20:30 | 2026-08-31 21:30 | Arun | GitHub | Completed | 1 | [14 empty] | 0 | bar: Day 13
US4 | T18 | Add MIT License to the team's GitHub repository | 2026-08-31 21:30 | 2026-08-31 22:00 | Anusha | Documentation | Completed | 0.5 | Day 13: 0.5 | 0
US4 | T19 | Prepare Agile documentation in repository as per reference Google Drive folder | 2026-09-01 10:00 | 2026-09-01 12:00 | Arun | Documentation | In Progress | 2 | Day 14: 2 | 12

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken